## Sheet1
INFORMATION ITEM: | [5 empty] | ATTACHMENT A
Clarion University
Information Items for April 21, 2016 Council of Trustees' Meeting
Status of Facilities Projects
| Project |  | Fund Source |  |  | Project Completion Date
Building |  | Number |  | Amount | Status
CLARION
Tippin Gym | Renovation/Construction | CL-696 | CA | 41900000 | RB | May-2018
Recreational Pool | Construction | CL-696 | AX | 4200000 | RB | Aug-2017
| Project Total |  |  | 46100000
Both Campuses | Accessibility Improvements | CL-759 | DM | 70000 | C
Marwick-Boyd | Fire Curtain & Improvements | CL-770 | DM | 280000 | UC | May-2016
Stevens/Moore Hall | ADA Accessibility Improvements | CL-775 | CA | 5000000 | AF | Sept-2017
Gemmell Student Center | Interior Design | CL-766 | AX | 1000000 | B | Sept-2016
Campus Electrical Upgrade | Upgrade for Additional Load | CL-774 | DM | 330000 | UC | May-2016
Campus Wide | Johnson Controls Upgrade |  | DM | 87600 | C | March-2016
Wilson Avenue Steam Tunnel | Replace Direct Bury Steam Lines | CL-783 | DM | 750000 | ID | Sept-2016
Still Hall | Roof Replacement | CL-786 | DM | 125000 | P | Sept-2016
Still Hall | Cooling Tower Replacement | CL-784 | DM | 98000 | P | Sept-2016
Marwick-Boyd | Roof Replacement | CL-787 | DM | 250000 | P | Sept-2016
Venango Suhr Library | Feasibility Study | CL-790 | SR |  | P
Source of Funds |  | Status
EG = Education & General Funds |  |  |  | P = Planning
AX = Auxiliary |  |  |  | ID = In Design
DM = Deferred Maintenance |  |  |  | B = Bidding/Contracting
CA = Capital Appropriation |  |  |  | UC = Under Construction
G = Grants |  |  |  | C = Complete
SA = Student Assessment |  |  |  | AF = Awaiting Funds
SR = Special Revenue (e.g., Parking Fees, etc.) |  |  |  | AS = Awaiting Scheduling
CL = Cancelled |  |  |  | RB = Rebid